## Annexure 7_1
Annexure 7_1
Progress of Computerisation in Regional Rural Banks
Sl. No | Name of the RRB | Branches | Sponsor Bank | State | Whether Computerisation & Internet Services provided | Status of Computerisation upto 31.12.2004 |  | Details thereof till present date | If not, when to be provided | Whether any Target in this respect Fixed | If so, details of achivements
[6 empty] | Head Office | Branches
1 | 2 | 3 | 4 | 5 | (a) | (b) | (c) | (d) | (e) | (f) | (g)
1 | BHAGIRATH GB | 107 | ALLAHABAD | UTTAR PRADESH | Yes | HO fully computerised with internet services | 56 | 65 branches computerised as on 9.8.05 | Another 15 branches by 31.3.2006 | Full computerised by 31.3.07 | As on 31.7.2005, 60.75% computerised.
2 | CHHATRASAL GB | 84 | ALLAHABAD | UTTAR PRADESH | Yes | HO fully computerised with internet services | 40 | 40 branches computerised as on 0.8.05 | Another 20 branches by 31.3.2006 | Total 60 branches by 31.3.06 | As on 9.8.2005, 47.06% computerised.
3 | SARAYU GB | 41 | ALLAHABAD | UTTAR PRADESH | Yes | HO fully computerised with internet services | 41 | 41 branches computerised 9.8.05. | Already computerised | Full | As on 9.8.2005, 100% computerised.
4 | SHARDA GB | 59 | ALLAHABAD | MADHYA PRADESH | Yes | HO fully computerised with internet services | 13 | 17 branches computerised as on 9.8.05. | Total 21 by 31.3.2006 | Total 21 branches by 31.3.06 | As on 31.3.2005, 28.81% computerised.
5 | SRAVASTI GB | 89 | ALLAHABAD | UTTAR PRADESH | Yes | HO 80% computerised | 12 | 22 branches computerised as on 9.8.05. | 32 branches by 31.3.2006 | Total 32 branches by 31.3.06 | As on 31.3.2005, 24.92% computerised.
6 | TULSI GB | 78 | ALLAHABAD | UTTAR PRADESH | Yes | 1 Dept. Computerised | 14 | 14 branches computerised as on 9.8.05. | 26 branches by 31.3.2006 | Total 26 branches and HO fully by 31.3.06 | As on 31.3.2005, 20.51% computerised.
7 | VINDHYAVASINI GB | 46 | ALLAHABAD | UTTAR PRADESH | Yes | HO fully computerised with internet services | 7 | 7 branches computerised as on 9.8.05. | 8 branches by 31.3.2006 | Total 15 branches by 31.3.06 | As on 31.3.2005, 15.22% computerised.
8 | CHAITANYA GB | 51 | ANDHRA | ANDHRA PRADESH | 25 branches computerised. | HO fully computerised with internet services | 25 | 25 branches computerised | By 2005-06 all branches to be computerised | Yes | Target (31.3.2005) = 26, Achievement = 25
9 | GODAVARI GB | 33 | ANDHRA | ANDHRA PRADESH | 25 branches computerised. | HO fully computerised with internet services | 25 | 25 branches computerised | By 2005-06 all branches to be computerised | Yes | Target (31.3.2005) = 25, Achievement = 25
10 | RUSHIKULYA GB | 75 | ANDHRA | ORISSA | 18 branches computerised. | HO fully computerised with internet services | 18 | 18 branches computerised | By 2005-06 all branches to be computerised | Yes | Target (31.3.2005) = 25, Achievement = 18
11 | ALLAHABAD KGB | 91 | B.O.B | UTTAR PRADESH | 108 are fully computerised, 64 partially computerised. Computer and Internet in Hos. No Internet in branches | HO fully computerised with internet services | 3 | 2 branches partially computerised and 1 fully computerised as on 29.7.05. | In respect of all these RRBs sponsored by BoB, 560 branches to be computerised by 3 1.03.2006 | 50% of total branches to be computerised before 31.3.2007 | 4 branches fully computerised as on 31.3.2005
12 | ARAVALI KGB | 60 | B.O.B | RAJASTHAN |  | HO fully computerised with internet services | 3 | 5 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 5 branches computerised as on 31.3.2005
13 | BAREILLY KGB | 81 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 7 | 9 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 11 branches computerised as on 31.3.2005
14 | BHILWARA-AJMER KGB | 53 | B.O.B | RAJASTHAN |  | HO fully computerised with internet services | 8 | 10 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 16 branches computerised as on 31.3.2005
15 | BUNDI-CHITTORGARH KGB | 63 | B.O.B | RAJASTHAN |  | HO fully computerised with internet services | 8 | 10 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 10 branches computerised as on 31.3.2005
16 | DUNGARPUR-BANSWARA KGB | 38 | B.O.B | RAJASTHAN |  | HO fully computerised with internet services | 4 | 1 partially computerised and 5 fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 6 branches computerised as on 31.3.2005
17 | FAIZABAD KGB | 67 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 7 | 9 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 9 branches computerised as on 31.3.2005
18 | FATEHPUR KGB | 51 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 1 | 1 branch fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 1 branch computerised as on 31.3.2005
19 | JHABUA-DHAR KGB | 90 | B.O.B | MADHYA PRADESH |  | HO fully computerised with internet services | 9 | 4 partially computerised and 7 fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 11 branches computerised as on 31.3.2005
20 | KANPUR KGB | 96 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 5 | 3 partially computerised and 4 fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 7 branches computerised as on 31.3.2005
21 | MARUDHAR KGB | 55 | B.O.B | RAJASTHAN |  | HO fully computerised with internet services | 2 | 2 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 8 branches computerised as on 31.3.2005
22 | NAINITAL-ALMORA KGB | 59 | B.O.B | UTTARANCHAL |  | HO fully computerised with internet services | 1 | 3 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 4 branches computerised as on 31.3.2005
23 | PANCHMAHAL GB | 48 | B.O.B | GUJARAT |  | HO fully computerised with internet services | 48 | 47 branches partially computerised and 1 fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 48 branches computerised as on 31.3.2005
24 | PRATAPGARH KGB | 71 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 1 | 3 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 4 branches computerised as on 31.3.2005
25 | RAEBARELI KGB | 69 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 2 | 4 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 4 branches computerised as on 31.3.2005
26 | SHAHJAHANPUR KGB | 36 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 4 | 6 branches fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 10 branches computerised as on 31.3.2005
27 | SULTANPUR KGB | 94 | B.O.B | UTTAR PRADESH |  | HO fully computerised with internet services | 2 | 1 branch partially computerised and 3 fully computerised as on 29.7.05. |  | 50% of total branches to be computerised before 31.3.2007 | 4 branches computerised as on 31.3.2005
28 | SURAT-BHARUCH GB | 34 | B.O.B | GUJARAT |  | HO fully computerised with internet services | 11 | 6 branches partially computerised and 7 fully computerised as on 29.7.05. |  | 50% of bank's total branches to be computerised before 31.3.2007 | 13 branches computerised as on 31.3.2005
29 | VALSAD-DANGS GB | 37 | B.O.B | GUJARAT |  | HO fully computerised with internet services | 16 | 18 branches fully computerised as on 29.7.05. |  | 50% of bank's total branches to be computerised before 31.3.2007 | 18 branches computerised as on 31.3.2005
30 | AVADH GB | 118 | B.O.I | UTTAR PRADESH | Yes | HO fully computerised | 100 | 100 branches computerised as on 4.8.05. | Already achieved | 120 branches will be computerised | 120 branches will be computerised
31 | BAITARANI GB | 96 | B.O.I | ORISSA | Yes | --- do --- | 42 | 42 branches computersied as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 42 branches computerised.
32 | BARABANKI GB | 92 | B.O.I | UTTAR PRADESH | Yes | --- do --- | 14 | 14 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 100% by 31.3.2005
33 | BHANDARA GB | 45 | B.O.I | MAHARASHTRA | Yes | --- do --- | 29 | 29 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 31 branches computerised.
34 | CHANDRAPUR-GADCHIROLI GB | 60 | B.O.I | MAHARASHTRA | Yes | --- do --- | 12 | 12 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 12 branches computerised.
35 | DEWAS-SHAJAPUR KGB | 56 | B.O.I | MADHYA PRADESH | Yes | --- do --- | 36 | 36 branches computerisedas on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 38 branches computerised.
36 | FARRUKHABAD GB | 81 | B.O.I | UTTAR PRADESH | Yes | --- do --- | 59 | 59 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 48 branches compuerised.
37 | GIRIDIH KGB | 27 | B.O.I | JHARKHAND | Yes | --- do --- | 9 | 9 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 13 branches computerised.
38 | HAZARIBAGH KGB | 30 | B.O.I | JHARKHAND | Yes | --- do --- | 14 | 14 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 18 branches computerised.
39 | INDORE-UJJAIN KGB | 36 | B.O.I | MADHYA PRADESH | Yes | --- do --- | 29 | 29 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 29 branches computerised.
40 | NIMAR KGB | 70 | B.O.I | MADHYA PRADESH | Yes | --- do --- | 24 | 24 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 24 branches computerised.
41 | RAJGARH-SEHORE KGB | 44 | B.O.I | MADHYA PRADESH | Yes | --- do --- | 35 | 35 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 35 branches computerised.
42 | RANCHI KGB | 78 | B.O.I | JHARKHAND | Yes | --- do --- | 7 | 7 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 7 branches computerised.
43 | RATNAGIRI-SINDHUDURG GB | 39 | B.O.I | MAHARASHTRA | Yes | --- do --- | 39 | 39 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | All 39 branches computerised.
44 | SINGHBHUM KGB | 76 | B.O.I | JHARKHAND | Yes | --- do --- | 12 | 12 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 12 branches computerised.
45 | SOLAPUR GB | 33 | B.O.I | MAHARASHTRA | Yes | --- do --- | 20 | 20 branches computerised as on 4.8.05. | All RRBs to achieve minimum 50% computerisation by March 2006. | All RRBs to achieve minimum 50% computerisation by March 2006. | 20 branches computerised.
46 | AURANGABAD-JALNA GB | 56 | B.O.M | MAHARASHTRA | All 56 branches fully computerised with no internet. | --- do --- | Completed | Computerised since September 2003. At present no internet as on 9.8.05. | No internet proposed. | NA | NA
47 | MARATHWWADA GB | 245 | B.O.M | MAHARASHTRA | Of 245, no branch computerised with no internet. | --- do --- | Not Done - Proposed | NA | Computerisation in Phase I to be completed by March 2006. Computerisation in Phase II to be completed by March 2007. | Computerisation in Phase I to be completed by March 2006. Computerisation in Phase II to be completed by March 2007. | 76 branches selected in Ist phase and remaining in 2nd phase.
48 | THANE GB | 21 | B.O.M | MAHARASHTRA | 18 branches computerised with no internet. | --- do --- | Partial | 18 branches computerised with no internet as on 9.8.05. | No internet proposed. | Out of remaining 3 branches one is proposed to be closed. Other 2 branches are provided hardware and Software | Data Entry is in progress. The computerisation of these 2 branches will be completed by August 2005
49 | MEWAR AGB | 58 | B.O.RAJ. | RAJASTHAN | Yes | --- do --- | Yes | 1 Internet connection available at Head Office. 39 Branches computerised. At 10 branches hardware has been supplied and work of master creation is in progress as on 9.8.05. | In remaining branches computerisation could not be considered for reasons viz. non-availability of electricity, etc. | Yes | March '06
50 | AKOLA GB | 47 | C.B.I | MAHARASHTRA | All HO of RRBs computerised with internet facility. No internet is provided to branches. | 8 | 24 | 24 branches computerised as on 4.8.05. | Remaining 23 branches to be computerised before March 2007 | Remaining 23 branches to be computerised before March 2007 | 24 branches computerised.
51 | BALLIA KGB | 87 | C.B.I | UTTAR PRADESH |  | 7 | 12 | 12 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2007 | 50% branches to be computerised before March 2007 | 12 branches computerised.
52 | BULDHANA GB | 24 | C.B.I | MAHARASHTRA |  | 4 | 24 | All 24 branches computerised as on 4.8.05. | NA (All branches computerised) | NA (All branches computerised) | All 24 branches compuerised.
53 | CHAMBAL KGB | 33 | C.B.I | MADHYA PRADESH |  | 4 | 33 | All 33 branches computerised as as 4.8.05. | NA (All branches computerised) | NA (All branches computerised) | All 33 branches compuerised.
54 | CHAMPARAN KGB | 143 | C.B.I | BIHAR |  | 3 | NIL | NIL | 50% branches to be computerised before March 2007 | 50% branches to be computerised before March 2007 | NIL
55 | CHHINDWARA-SEONI KGB | 61 | C.B.I | MADHYA PRADESH |  | 7 | 40 | 40 branches computerised as on 4.8.05 | Remaining 21 branches to be computerised before March 2007 | Remaining 21 branches to be computerised before March 2007 | 40 branches computerised.
56 | ETAWAH KGB | 50 | C.B.I | UTTAR PRADESH |  | 2 | 10 | 10 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2007 | 50% branches to be computerised before March 2007 | 10 branches computerised.
57 | GOPALGANJ KGB | 59 | C.B.I | BIHAR |  | 10 | 7 | 7 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2007 | 50% branches to be computerised before March 2007 | 7 branches computerised.
58 | GWALIOR-DATIA KGB | 30 | C.B.I | MADHYA PRADESH |  | 3 | 22 | 22 branches computerised as on 4.8.05. | Remaining 8 branches to be computerised before March 2007 | Remaining 8 branches to be computerised before March 2007 | 22 branches computerised.
59 | HADOTI KGB | 80 | C.B.I | RAJASTHAN |  | 8 | 46 | 46 branches computerised as on 4.8.05. | Remaining 34 branches to be computerised before March 2007 | Remaining 34 branches to be computerised before March 2007 | 46 branches computerised.
60 | KGB HOSHANGABAD | 80 | C.B.I | MADHYA PRADESH |  | 8 | 25 | 25 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 25 branches computerised.
61 | KOSI KSH GB | 164 | C.B.I | BIHAR |  | 8 | NIL | NIL | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | NIL
62 | MADHUBANI KGB | 89 | C.B.I | BIHAR |  | 3 | NIL | NIL | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | NIL
63 | MANDLA-BALAGHAT KGB | 54 | C.B.I | MADHYA PRADESH |  | 8 | 18 | 18 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 18 branches computerised.
64 | MITHILA KGB | 79 | C.B.I | BIHAR |  | 3 | 8 | 8 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 8 branches computerised.
65 | RATLAM-MANDSAUR KGB | 40 | C.B.I | MADHYA PRADESH |  | 12 | 40 | All 40 branches computerised as on 4.8.05. | NA (All branches computerised) | NA (All branches computerised) | All 40 branches computerised.
66 | SARAN KGB | 64 | C.B.I | BIHAR |  | 2 | 2 | 2 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 2 branches computerised.
67 | SHAHDOL KGB | 42 | C.B.I | MADHYA PRADESH |  | 5 | 12 | 17 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 12 branches computerised.
68 | SIWAN KGB | 71 | C.B.I | BIHAR |  | 1 | 16 | 16 branches computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 16 branches computerised.
69 | SURGUJA KGB | 83 | C.B.I | CHHATTISGARH |  | 8 | 40 | 40 branches computerised as on 4.8.05 | Remaining 43 branches to be computerised before March 2007 | Remaining 43 branches to be computerised before March 2007 | 40 branches computerised.
70 | UTTAR BANGA KGB | 114 | C.B.I | WEST BENGAL |  | 11 | 1 | 1 branch computerised as on 4.8.05. | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | 1 branch computerised.
71 | VAISHALI KGB | 188 | C.B.I | BIHAR |  | 1 |  | NIL | 50% branches to be computerised before March 2009 | 50% branches to be computerised before March 2009 | NIL
72 | YAVATMAL GB | 23 | C.B.I | MAHARASHTRA |  | 2 | 18 | 18 branches computerised as on 4.8.05. | Remaining 5 branches to be computerised before March 2007 | Remaining 5 branches to be computerised before March 2007 | 18 branches computerised.
73 | ALIGARH KGB | 86 | CANARA | UTTAR PRADESH | Yes | 4 | 25 | 25 computerised as on 6.6.05. | 55 branches to be computerised | 55 branches to be computerised during current financial year | 25 computerised.
74 | CHITRADURGA GB | 91 | CANARA | KARNATAKA | Yes | 4 | 26 | 26 computerised as ib 6.6.05. | 61 branches to be computerised | 61 branches to be computerised | 26 computerised.
75 | ETAH GB | 58 | CANARA | UTTAR PRADESH | Yes | 3 | 10 | 10 computerised as on 6.6.05. | 25 branches to be computerised | 25 branches to be computerised | 10 computerised.
76 | JAMUNA GB | 39 | CANARA | UTTAR PRADESH | Yes | 3 | 39 | 39 computerised and 3 HO and AO computerised as on 6.6.05. | - | - | 39 computerised and 3 HO and AO computerised.
77 | KOLAR GB | 61 | CANARA | KARNATAKA | Yes | 3 | 44 | 44 computerised as on 6.6.05. | 17 branches be computerised during current financial year. | 17 branches be computerised during current financial year. | 44 computerised.
78 | SAHYADRI GB | 29 | CANARA | KARNATAKA | Yes | 1 | 27 | 27 branches computerised as on 6.6.05. | 2 branches to be computerised during current financial year | 2 branches to be computerised during current financial year | 27 computerised
79 | SOUTH MALABAR GB | 210 | CANARA | KERALA | Yes | 9 | 62 | 62 computerised and 3 HO and AO computerised as on 6.6.05. | 75 branches to be computerised during current financial year | 75 branches to be computerised during current financial year | 62 computerised and 3 HO and AO computerised
80 | TUNGABHADRA GB | 162 | CANARA | KARNATAKA | Yes | 8 | 4 | 4 computerised and 4 HO and AO computerised as on 6.6.05. | 59 branches to be computerised during current financial year | 59 branches to be computerised during current financial year | 4 computerised and 4 HO and AO computerised
81 | CHICKMAGALUR-KODAGU GB | 50 | CORPN | KARNATAKA | Computerisation at large scale undertaken. | 1 | 6 | 6 branches and HO fully computerised. Back office computerisation provided to another 9 branches. | 40 branches to be computerised before end March 2006. | 40 branches to be computerised before end March 2006. | 1 Head Office and 7 Branches
82 | BANASKANTHA-MEHSANA GB | 68 | DENA | GUJARAT | 61 branches computerised without internet. | Computerised | 54 | 61 branches computerised without internet.# (#7 more branches computerised during 1.1.2005 to 31.3.2005) | All branches by end December 2005 without internet facility | Yes | All the 68 branches by 2005-06
83 | DURG-RAJNANDGAON GB | 101 | DENA | CHHATTISGARH | 20 branches computerised without internet. | Computerised | 19* (* Status of the computerisation of the branches as of 31.12.2004) | 20 branches computerised without internet. ## ( ## 1 more branch computerised during 1.1.2005 to 31.3.2005) | 60 branches till 2007 without internet facility | Yes | Cumulative Target: 2005-06= 40 branches, 2006-07= 60 branches
84 | KUTCH GB | 34 | DENA | GUJARAT | 25 branches computerised without internet. | Computerised | 25* (* Status of the computerisation of the branches as of 31.12.2004) | 25 branches computerised without internet as on 26.7.05. | All branches till 2007 without internet facility | Yes | Cumulative Target: 2004-05=30 branches, 2006-07= all branches
85 | SABARKANTHA-GANDHINAGAR GB | 27 | DENA | GUJARAT | All 27 branches computerised without internet. | Computerised | 27* (* Status of the computerisation of the branches as of 31.12.2004) | All 27 branches computerised without internet as on 26.7.05. | All the branches have already been computerised. No plans to provide interent to branches. | Not applicable. | Not applicable.
86 | DHENKANAL GB | 52 | I.O.B | ORISSA | Yes | Computerised | 50 | 50 branches computerised as on 6.8.05. | Remaining branches to be computerised in the current year. | Remaining branches to be computerised in the current year. | 50 branches computerised
87 | PANDYAN GB | 165 | I.O.B | TAMILNADU | Yes | Computerised | 123 | All 165 branches computerised as on 6.8.05. | NA | NA
88 | PURI GB | 113 | I.O.B | ORISSA | Yes | Computerised | 44 | 50 branches computerised as on 6.8.05. | Remaining branches to be computerised in the current year. | Remaining branches to be computerised in the current year. | 50 branches computerised.
89 | ADHIYAMAN GB | 24 | INDIAN | TAMILNADU | Head Offices of RRB were computerised with internet | HO computerised. Internet facilities provided | All 24 branches computerised | All 24 branches computerised as on 3.8.05. | NA | NA | 100%
90 | KANAKADUGRA GB | 29 | INDIAN | ANDHRA PRADESH |  | HO computerised. Internet facilities provided | All 29 branches computerised | All 29 branches computerised as on 3.8.05. | NA | NA | 100%
91 | SHRI VENKETESHWARA GB | 75 | INDIAN | ANDHRA PRADESH |  | HO computerised. Internet facilities provided | 67 branches computerised | 67 branches computerised as on 3.8.05. | Within the first quarter of 2005-06 | Remaining 8 * branches to be computerised before 31.3.2005. (*As on date all 75 branches are computerised) | 100%
92 | VALLALAR GB | 24 | INDIAN | TAMILNADU |  | HO computerised. Internet facilities provided | All 24 branches computerised | All 24 branches computerised as on 3.8.05. | NA | NA | 100%
93 | JAMMU RB | 90 | J&K BANK | JAMMU & KASHMIR | Branches not computerised. Partial computerisation of HO | Partially computerised | NIL | Branches not computerised with Partial computerisation of HO as on 3.8.05. | 5 branches and 3 Area Offices to be computerised during current financial year. | 5 branches and 3 Area Offices to be computerised during current financial year. | Branches not computerised with Partial computerisation of HO
94 | KAMRAZ RB | 78 | J&K BANK | JAMMU & KASHMIR | Branches not computerised. Partial computerisation of HO | Partially computerised | NIL | Branches not computerised with Partial computerisation of HO as on 3.8.05. | 4 branches to be computerised during current financial year. | 4 branches to be computerised during current financial year. | Branches not computerised with Partial computerisation of HO
95 | FARIDKOT-BHATINDA KGB | 22 | P&S BK | PUNJAB | All branches computerised. | Partially computerised | All 22 branches computerised | All 22 branches and 1 HO computerised as on 4.8.05. | NA | NA | All 22 branches and HO computerised.
96 | ALWAR-BHARATPUR AGB | 88 | P.N.B | RAJASTHAN | Computerisation-Yes / Internet - No | Yes | 45 | 45 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 45
97 | AMBALA KURUKSHETRA GB | 39 | P.N.B | HARYANA | Computerisation-Yes / Internet - No | Yes | 39 | 39 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 39
98 | BHOJPUR ROHTAS GB | 157 | P.N.B | BIHAR | Computerisation-Yes / Internet - No | Yes | 66 | 66 branches computerised as on 9.8.05 | - | 50% of branches, HO and AO | 66
99 | DEVI PATAN KGB | 75 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 38 | 38 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 38
100 | GURDASPUR-AMRITSAR KGB | 60 | P.N.B | PUNJAB | Computerisation-Yes / Internet - No | Yes | 36 | 36 branches computerisedas on 9.8.05. | - | 50% of branches, HO and AO | 36
101 | HARYANA KGB | 90 | P.N.B | HARYANA | Computerisation-Yes / Internet - No | Yes | 45 | 45 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 90
102 | HIMACHAL GB | 108 | P.N.B | HIMACHAL PRADESH | Computerisation-Yes / Internet - No | Yes | 53 | 53 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 53
103 | HINDON GB | 22 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 6 | 6 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 9
104 | HISSAR-SIRSA KGB | 50 | P.N.B | HARYANA | Computerisation-Yes / Internet - No | Yes | 45 | 45 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 50
105 | KAPURTHALA-FEROZPUR KGB | 46 | P.N.B | PUNJAB | Computerisation-Yes / Internet - No | Yes | 45 | 45 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 46
106 | KISAN GB | 55 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 17 | 17 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 17
107 | MAGADH GB | 165 | P.N.B | BIHAR | Computerisation-Yes / Internet - No | Yes | 32 | 32 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 32
108 | MUZAFFARNAGAR KGB | 25 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 15 | 15 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 15
109 | NALANDA GB | 66 | P.N.B | BIHAR | Computerisation-Yes / Internet - No | Yes | 20 | 20 branches computerised as on 9.8.05. | - | 50% of branches, HO and AO | 20
110 | PATALIPUTRA GB | 19 | P.N.B | BIHAR | Computerisation-Yes / Internet - No | Yes | 10 | 10 branches computerised as on 4.8.05. | - | 50% of branches, HO and AO | 10
111 | RANI LAKSHMI BAI KGB | 43 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 10 | 10 branches computerised as on 4.8.05. | - | 50% of branches, HO and AO | 10
112 | SHEKHAWATI GB | 108 | P.N.B | RAJASTHAN | Computerisation-Yes / Internet - No | Yes | 53 | 53 branches computerised as on 4.8.05. | - | 50% of branches, HO and AO | 93
113 | SHIVALIK KGB | 41 | P.N.B | PUNJAB | Computerisation-Yes / Internet - No | Yes | 22 | 22 branches computerised as on 4.8.05. | - | 50% of branches, HO and AO | 24
114 | VIDUR GB | 41 | P.N.B | UTTAR PRADESH | Computerisation-Yes / Internet - No | Yes | 40 | 40 branches computerised as on 4.8.05 | - | 50% of branches, HO and AO | 41
115 | BIKANER KGB | 27 | S.B.B.J | RAJASTHAN | NO | NIL | NIL | NA | 2005-2006 HO + 12 branches to be computerised. Internet will be provided after full computerisation takes place. | HO + 12 branches | 3 branches computerised upto 30.5.2005 / 05 branches upto 31.7.05
116 | MARWAR GB | 135 | S.B.B.J | RAJASTHAN | NO | NIL | NIL | NA | 2005-2006 HO + 67 branches to be computerised. Internet will be provided after full computerisation takes place. | HO + 67 | 6 branches computerised upto 30.5.2005 / 12 branches upto 31.7.05
117 | SRIGANGANAGAR KGB | 43 | S.B.B.J | RAJASTHAN | NO | NIL | NIL | NA | 2005-2006 HO + 23 branches to be computerised. Internet will be provided after full computerisation takes place. | HO + 23 | 4 branches computerised upto 30.5.2005 / 8 branches upto 31.7.05
118 | GOLCONDA GB | 23 | S.B.H | ANDHRA PRADESH | Only in few branches computerisation completed with no internet facility. | No | 16 | 16 branches computerised as on 27.8.05. | HO & remaining 7 branches to be computerised in 2005-06 & 2006-07 | 7 branches to be computerised in 2005-06 | 16 branches computerised.
119 | SHRI SATHAVAHANA GB | 46 | S.B.H | ANDHRA PRADESH | Only in few branches computerisation completed with no internet facility. | No | 10 | 10 branches computerised as on 27.8.05. | HO & remaining 35 branches to be computerised in 2005-06 & 2006-07 | 35 branches to be computerised in 2005-06 | 10 branches computerised.
120 | SRI SARASWATHI GB | 70 | S.B.H | ANDHRA PRADESH | Only in few branches computerisation completed with no internet facility. | No | 8 | 8 branches computerised as on 27.8.05. | HO & 50 branches to be computerised in 2005-06 | 50 branches to be computerised in 2005-06 | 8 branches computerised.
121 | SRIRAMA GB | 27 | S.B.H | ANDHRA PRADESH | Only in few branches computerisation completed with no internet facility. | No | 6 | 6 branches computerised as on 27.8.05. | HO & 21 branches to be computerised in 2005-06 & 2006-07 | 21 branches to be computerised in 2005-06 | 6 branches computerised.
122 | ALAKNANDA GB | 45 | S.B.I | UTTARANCHAL | 237 computerised | Yes | 2 completed | 237 computerised as on 2.8.05. | Computerisation of 157 branches in process | Each RRB has drawn out a five year plan for computerisation | Each RRB has drawn out a five year plan for computerisation
123 | ARUNACHAL PRADESH RB | 17 | S.B.I | ARUNACHAL PRADESH |  | Yes | Nil
124 | BASTAR KGB | 55 | S.B.I | CHHATTISGARH |  | Yes | 6 completed (12 in pipeline)
125 | BASTI GB | 105 | S.B.I | UTTAR PRADESH |  | Yes | 5 completed (20 in pipeline)
126 | BILASPUR-RAIPUR KGB | 137 | S.B.I | CHHATTISGARH |  | Yes | Nil
127 | BOLANGIR AGB | 156 | S.B.I | ORISSA |  | Yes | 1 completed (2 in pipeline)
128 | BUNDELKHAND KGB | 83 | S.B.I | MADHYA PRADESH |  | Yes | Nil
129 | DAMOH-PANNA-SAGAR KGB | 71 | S.B.I | MADHYA PRADESH |  | Yes | 20 completed (15 in pipeline)
130 | ELLAQUI DEHATI BANK | 98 | S.B.I | JAMMU & KASHMIR |  | Yes | Nil
131 | GANGA-YAMUNA GB | 39 | S.B.I | UTTARANCHAL |  | Yes | Nil completed (2 in pipeline)
132 | GORAKHPUR KGB | 200 | S.B.I | UTTAR PRADESH |  | Yes | 21 completed (9 in pipeline)
133 | KAKATHIYA GB | 40 | S.B.I | ANDHRA PRADESH |  | Yes | All completed
134 | KALAHANDI AGB | 77 | S.B.I | ORISSA |  | Yes | 3 completed (4 in pipeline)
135 | KHASI JAINTIA RURAL KA BK | 51 | S.B.I | MEGHALAYA |  | Yes | 5 completed (5 in pipeline)
136 | KORAPUT PANCHABATI GB | 90 | S.B.I | ORISSA |  | Yes | 1 completed (7 in pipeline)
137 | KRISHNA GB | 106 | S.B.I | KARNATAKA |  | Yes | 21 (12 in pipeline)
138 | LANGPI DEHANGI RB | 43 | S.B.I | ASSAM |  | Yes | Nil completed (11 in pipeline)
139 | MANJIRA GB | 64 | S.B.I | ANDHRA PRADESH |  | Yes | 34 completed
140 | MIZORAM RB | 54 | S.B.I | MIZORAM |  | Yes | 2 completed (8 in pipeline)
141 | NAGALAND RB | 8 | S.B.I | NAGALAND |  | Yes | Nil
142 | NAGARJUNA GB | 147 | S.B.I | ANDHRA PRADESH |  | Yes | 35 completed (15 in pipeline)
143 | PALAMAU KGB | 75 | S.B.I | JHARKHAND |  | Yes | Nil completed
144 | PARVATIYA GB | 27 | S.B.I | HIMACHAL PRADESH |  | Yes | Nil completed
145 | PITHORAGARH KGB | 25 | S.B.I | UTTARANCHAL |  | Yes | 4 completed (5 in pipeline)
146 | RAIGARH KGB | 60 | S.B.I | CHHATTISGARH |  | Yes | 1 completed (2 in pipeline)
147 | SAMASTIPUR KGB | 73 | S.B.I | BIHAR |  | Yes | Nil completed
148 | SANGAMESHWRA GB | 73 | S.B.I | ANDHRA PRADESH |  | Yes | 36 completed (12 in pipeline)
149 | SANTHAL PARGANAS GB | 103 | S.B.I | JHARKHAND |  | Yes | Nil completed
150 | SHIVPURI-GUNA KGB | 58 | S.B.I | MADHYA PRADESH |  | Yes, Partially | 5 completed
151 | SRI VISAKHA GB | 163 | S.B.I | ANDHRA PRADESH |  | Yes | 35 completed (16 in pipeline)
152 | VIDISHA-BHOPAL KGB | 23 | S.B.IND | MADHYA PRADESH | Back office computerisation of all branches complete while front office being computerised. Internet available at HO only | Compilation work is done by outsourced agency. | Back office computerisation of all branches complete while front office being computerised. Internet available at HO only | Back office computerisation of all branches complete while front office computerisation is in progress as on 2.9.05. | Front office computerisation to be completed by March 2006. | Front office computerisation to be completed by March 2006. | Software has been finalised. Expected to computerise all the branches by March 2006.
153 | CAUVERY GB | 125 | S.B.M | KARNATAKA | 50 branches computerised, no internet. | 4 | 50 | 40 branches computerised, no internet as on 3.8.05. | 86 branches by March 2006. | 86 branches by March 2006. | 50 branches as on 2004-05
154 | KALPATHARU GB | 79 | S.B.M | KARNATAKA | 40 branches computerised, no internet. | 11 | 40 | 40 branches computerised, no internet as on 3.8.05. | 10 branches by March 2005 / 29 branches by March 2007. | 29 branches by March 2007. | 50 branches as on 2004-05
155 | MALWA GB | 41 | S.B.P | PUNJAB | Head Office & 10 branches since computerised in current year as on 31.7.2005. Internet services not provided | NIL | NIL | No branch computerised upto Dec.2004 | Head Office & 10 branches since computerised in current year as on 31.7.2005 | All remaining 31 branches to be computerised by 30.9.2005 | Head Office & 10 branches since computerised in current year as on 31.7.2005
156 | JAMNAGAR GRAMIN BK | 53 | S.B.S | GUJARAT | All the branches and their Hos fully computerised. | 1 | 53 | All 53 branches and HO computerised | NA | NA | All 53 branches and HO computerised
157 | JUNAGADH-AMRELI GB | 39 | S.B.S | GUJARAT | All the branches and their Hos fully computerised. | 1 | 34 | All 34 branches and HO computerised | NA | NA | All 34 branches and HO computerised
158 | SURENDRANAGAR-BHAVNAGAR GB | 43 | S.B.S | GUJARAT | All the branches and their Hos fully computerised. | 1 | 43 | All 43 branches and HO computerised. Internet in HO. | NA | NA | All 43 branches and HO computerised. Internet in HO.
159 | BIJAPUR GB | 91 | SYNDICATE | KARNATAKA | Computerisation and internet services provided. | Computerised | 70 branches computerised | 70 branches computerised as on 2.8.05. | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 70 branches computerised.
160 | GURGAON GB | 121 | SYNDICATE | HARYANA | Computerisation and internet services provided. | Computerised | 78 branches computerised. | 78 branches computerised as on 2.8.05. | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 78 branches computerised.
161 | MALAPRABHA GB | 243 | SYNDICATE | KARNATAKA | Computerisation and internet services provided. | Computerised | 218 branches computerised. | 218 branches computerised as on 2.8.05. | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 218 branches computerised.
162 | NETRAVATI GB | 22 | SYNDICATE | KARNATAKA | Computerisation and internet services provided. | Computerised | All 22 branches computerised. | All 22 branches computerised. | NA | NA | All 22 branches computerised.
163 | NORTH MALABAR GB | 152 | SYNDICATE | KERALA | Computerisation and internet services provided. | Computerised | All 152 branches computerised. | All 152 branches computerised. | NA | NA | All 152 branches computerised.
164 | PINAKINI GB | 101 | SYNDICATE | ANDHRA PRADESH | Computerisation and internet services provided. | Computerised | 100 branches computerised. | 100 branches computerised as on 2.8.05. | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 100 branches computerised.
165 | PRATHAMA BANK | 170 | SYNDICATE | UTTAR PRADESH | Computerisation and internet services provided. | Computerised | 125 branches computerised. | 125 branches computerised as on 2.8.05 | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 125 branches computerised.
166 | RAYALSEEMA GB | 148 | SYNDICATE | ANDHRA PRADESH | Computerisation and internet services provided. | Computerised | All 148 branches computerised. | All 148 branches computerised. | NA | NA | All 148 branches computerised.
167 | SREE ANANTHA GB | 81 | SYNDICATE | ANDHRA PRADESH | Computerisation and internet services provided. | Computerised | 80 branches computerised. | 80 branches computerised as on 2.8.05. | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 80 branches computerised.
168 | VARADA GB | 31 | SYNDICATE | KARNATAKA | Computerisation and internet services provided. | Computerised | 30 branches computerised |  | 100% computerisation to be achieved by March 2006. | 100% computerisation to be achieved by March 2006. | 30 branches computerised.
169 | CACHAR GB | 44 | U.B.I | ASSAM | Yes, Without Internet | Partly with 2 computers | 3 | HO-2 computers operational - Branches - 2 branches operational and 1 branch under process as on 2.9.05. |  | 6 branches by 2005-06 | HO - 3computers - Br-7 ALPMs in 3 branches
170 | GAUR GB | 146 | U.B.I | WEST BENGAL | Yes, with internet at HO | Parly computerised | 5 | HO partly operational - Branch - Master Creation (MC) started in 5 branches |  | 5 branches by 2005-06 | HO partly - Br-ALPM introduced in 5 branches out of which 4 branches functioning
171 | LAKHIMI GB | 102 | U.B.I | ASSAM | Yes, with internet at HO | Computerised and 4 Area Office computerised | 8 | HO operational - Br.operational 2.9.05. |  | To cover 43 branches by 2008-09 | HO, Area Office and 14 branches computerised and 21 branches under process
172 | MALLABHUM GB | 179 | U.B.I | WEST BENGAL | Yes, with internet at HO | Partly with LAN | Complete in 1 Branch - Under process in 2 Branches | HO-CM,GM Office and 7 Departments as on 2.9.05. |  | 10 branches by 2005-06 and 50 branches by 2009 | HO-CM,GM Office and 7 Departments - Branches - 3 fully computerised and 1 with Back Office
173 | MANIPUR RB | 29 | U.B.I | MANIPUR | Partly at HO with Internet | 3 Computers with LAN | 3 | HO - 2 PC with LAN - Branches-1 branch parallel run with 2 branches Master File Creation going on as on 2.9.05. |  | 1 branch by 2005-06 | HO - 2 PC with LAN - Branches-1 branch parallel run with 2 branches Master File Creation going on
174 | MURSHIDABAD GB | 40 | U.B.I | WEST BENGAL | Yes at HO without Internet | Partly (1 Deptt. At HO) | 2 | HO - 1 Deptt. Partially computerised - Br-ALPM system provided as on 2.9.05. |  | 7 branches by March 2006 | HO - 1 Deptt. Partially computerised - Br-ALPM system provided -Branches-computer provided to 3 branches
175 | NADIA GB | 67 | U.B.I | WEST BENGAL | Yes - Internet at HO only | Computerised | 8 | HO computerised - 8 branches computerised as on 2.9.05. |  | 26 branches by 31 March 2007 | HO computerised - 8 branches computerised
176 | PRAGJYOTISH GB | 165 | U.B.I | ASSAM | Yes- Internet at HO and Fancy Bazaar Branch computerised | Computerised | 12 | HO computer installed in all Divisions with network - Branches-3 TBM and 2 on-line and 7 with parallel run as on 2.9.05. |  | 30 branches by 30 June 2006 | HO computer installed in all Divisions with network - Branches-3 TBM and 20 ALMP (2 online - 7 with parallel run and MC progressing in 11)
177 | SAGAR GB | 115 | U.B.I | WEST BENGAL | HO fully computerised | Computerised | 5 | HO - 7 Computers - Branches - Hardware and software supplied in 5 branches as on 2.9.05. |  | 3 branches by 2005 and 5 branches by 31.3.2006 | HO operational - 2 branches computerised
178 | SUBANSIRI GB | 45 | U.B.I | ASSAM | Yes with Internet at HO | All 5 Deptt.s are computerised | 4 | HO computerised - 4 branches computerised as on 2.9.05. |  | 11 branches by 31.3.2006. | HO computerised -11 branches computerised
179 | TRIPURA GB | 87 | U.B.I | TRIPURA | Partly | HO not computerised | 4 | HO - PCs arrived not yet installed - Branches - Only 1 branch Online as on 2.9.05. |  | 20 Branches by 2005-06 | HO - 2 PCs installed - 3 yet to be installed - Branches - 4 branches online - MC started in 4 branches and 4 PC ordered
180 | BALASORE GB | 62 | U.C.O | ORISSA | Yes | Yes | NIL | Head Office only | 2004-05 | Head office and15 branches | Head Office
181 | BARDHAMAN GB | 90 | U.C.O | WEST BENGAL | Yes | Yes | NIL | Internet at H.O. | 2004-05 | Head office and 26 branches | Head Office
182 | BEGUSARAI KGB | 21 | U.C.O | BIHAR | Yes | Yes | Yes | 6 branches and Head Office as on 4.8.05. | 2004-05 | Head office and 6 branches | 6 branches and H.O
183 | BHAGALPUR-BANKA KGB | 24 | U.C.O | BIHAR | Yes | Yes | NIL | Head Office. | 2004-05 | Head Office and 7 branches | Head Office
184 | CUTTACK GB | 121 | U.C.O | ORISSA | Yes | Yes | NIL | 4 PC in H.O as on 4.8.05. | 2004-05 | Head Office | Head Office
185 | HOWRAH GB | 59 | U.C.O | WEST BENGAL | Yes | Yes | NIL | Internet at H.O. | 2004-05 | Head Office, 2 Area Office and 1 branch | Head Office
186 | JAIPUR NAGAUR AGB | 144 | U.C.O | RAJASTHAN | Yes | Yes | Yes | 5 Area Office, 6 branches and HO as on 4.8.05. | 2004-05 | 16 Branches, 5 Area Office and HO | 6 branches, 5 Area Offices & HO
187 | MAHAKAUSHAL KGB | 42 | U.C.O | MADHYA PRADESH | Yes | Yes | Yes | 19 branches and HO as on 4.8.05. | 2004-05 | Head Office and 22 branches | 19 branches & H.O
188 | MAYURAKSHI GB | 65 | U.C.O | WEST BENGAL | Yes | Yes | Yes | 2 branches and Internet at Head office as on 4.8.05. | 2004-05 | Head Office and 5 branches | 2 branches and H.O
189 | MONGHYR KGB | 106 | U.C.O | BIHAR | Yes | Yes | Yes | 5 branches and Internet at Head Office as on 4.8.05. | 2004-05 | Head Office and 10 branches | 5 branches & H.O
190 | THAR AGB | 66 | U.C.O | RAJASTHAN | Yes | Yes | NIL | Internet at H.O. | 2004-05 | Head Office and 6 branches | Head Office
191 | KSHETRIYA KISAN GB | 63 | U.P.S.C.B | UTTAR PRADESH | No branch computerised | Not yet been done in the Bank | Not yet been done in the Bank | As of 6.8.05 computeisation not yet done in the Bank | UPCB advised that the issue of computerisation will be discussed in the ensuing review meeting of the bank on 13 August 2005 | No | NA
192 | GOMTI GB | 84 | UNION | UTTAR PRADESH | 35 branches and 1 extension counter partially computerised. | Head Office & 2 Area Offices computerised | 35 + 1 extension counter | 35 branches and 1 extension counter partially computerised. Internet only at the H.O as on 18.8.05. | 2004-05 and 2005-06 = 35 branches + 1 extension counter, 2006-07 =14 branches | Yes | Target (March 06) = 84 branches Achievement = 35 branches and 1 extension counter
193 | KASHI GB | 82 | UNION | UTTAR PRADESH | 59 branches partially computerised. | Head Office computerised | 59 | 59 branches partially computerised as on 18.8.05. Internet only at HO | Remaining 23 branches by September 2005. | Yes | Target (March 06) = 82 branches Achievement = 61 branches
194 | REWA-SIDHI GB | 82 | UNION | MADHYA PRADESH | 18 branches partially computerised | Nil | 18 | 18 branches partially computerised. Internet not provided as on 18.8.05. | By 2005-06, 41 branches to be computerised | Yes | Target (March 06) = 41 branches Achievement = 22 branches
195 | SAMYUT KGB | 168 | UNION | UTTAR PRADESH | 100 branches partially computerised | Head Office & 6 Area Offices computerised | 100 | 100 branches partially computerised. Internet not available | By 2005-06, remaining 68 branches to be computerised | Yes | Target (March 06) = 168 branches Achievement = 105 branches
196 | VISVESHWARAYA GB | 25 | VIJAYA | KARNATAKA | Partially computerised. No internet. | Partially computerised | 24 branches have been partially computerised (Back office computerisation completed) One Branch is fully computerised. | 24 branches have been partially computerised. (Back office computerisation completed). One Branch is fully computerised as on 5.8.05. | 7 more branches are proposed to be fully computerised during the next 3-4 months. | 7 more branches are proposed to be fully computerised during the next 3-4 months. Remaining branches will be fully computerised in a phased manner. | Proposed to fully computerise all the branches over the next two years.